#### 1. Review and Align Contractor Proposals

- Task: Evaluate each contractor’s menu proposal to ensure it aligns with your pricing tiers ($14 Budget, $17 Core, $20 Premium) and offers dietary-friendly options (e.g., vegan, gluten-free).

- Details: Confirm contractors specify their chosen tier(s) and availability dates, as they’re not required to offer all tiers or work every date. For example, Five Course Provisions’ $20 Premium proposal should be assessed for potential Budget or Core options to appeal to varied budgets.

- Deadline: May 13, 2025.

- Tool: Use Google Forms (free) to collect standardized menu submissions.

#### 2. Negotiate Minimum Order Sizes

- Task: Discuss minimum order requirements with contractors to ensure flexibility for smaller events (50–100 guests).

- Details: For contractors like Five Course Provisions (75-box minimum), negotiate a 50-box minimum to align with Sarah Nguyen’s typical event sizes, increasing order frequency.

- Deadline: May 15, 2025.

#### 3. Finalize and Sign Contractor Agreements

- Task: Sign the Independent Contractor Agreement with each chef once their proposals are approved.

- Details: Ensure agreements reflect the flexibility for contractors to choose tiers and dates, as updated in your contract. Verify all terms (e.g., 80/10/10 split, net 30 payments) are clear.

- Deadline: May 20, 2025.

#### 4. Create a Menu and Availability Tracking System

- Task: Set up a system to track each contractor’s menu tiers, availability, and minimum order requirements.

- Details: This ensures you can quickly match contractors to customer inquiries (e.g., Sarah’s request for a $17 Core meal for 60 guests).

- Deadline: May 22, 2025.

- Tool: Use Google Sheets (free) or HubSpot CRM (free tier) for tracking.

#### 5. Launch Initial Marketing Campaign

- Task: Promote your catering services, highlighting the diverse menus and tiered pricing options.

- Details: Update your catering page on Culinary Block and create Instagram Reels showcasing contractor menus (e.g., Five Course Provisions’ Latin American dishes). Offer a 10% first-order discount to attract Sarah’s tech firms.

- Deadline: May 27, 2025.

- Tool: Use Canva (free) for Reels and Mailchimp for email campaigns.